Particular Conditions - Part B: Special Provisions

The following Particular Conditions amend and/or add to the General Conditions as and where noted. These Particular Conditions take Precedence over the General Conditions.

1)	Sub-Clause 1.1.2 - delete the text next to the Sub-Clause and replace with:

“Not used. Any references to Base Data in the Contract shall be deemed to refer to the signing date of the Contract if the context allows and shall in any other case be deemed to be null and void.”

2)	Sub-Clause 1.1.4 - delete the text next to the Sub-Clause and replace with:

“Commencement Date” means the date mentioned in the Contract Agreement.”

3)	Sub-Clause 1.1.10 – add sentence with the following text:

“The Contract Price is exclusive of VAT, which shall be added, if applicable, according to the Laws. All duties, levies and / or taxes of whatever nature are included in the Contract Price.”

4)	Sub-Clause 1.1.16 – delete the text next to the Sub-Clause and replace with:

“Cost” means all expenditure reasonably incurred by the Contractor, whether on or off the Site and which is fully justified by supported documents and does not include profit. Where the Contractor is entitled under a Sub-Clause of these Conditions to payment of Cost, it shall be in addition to the Contract Price.”

5)	Sub-Clause 1.1.17 – delete the text next to the Sub-Clause and replace with:

“Not used. Any references to “Cost Plus Profit” shall be read and interpreted by the Parties as references to “Cost” and no profit shall be added to the “Cost”.

6)	Sub-Clause 1.1.19 - delete the text next to the Sub-Clause and replace with:

“Not used. Any references to DAAB or Dispute Avoidance/Adjudication Board in the Contract shall be deemed null and void and have no legal standing between the Employer and the Contractor.”

7)	Sub-Clause 1.1.20 - delete the text next to the Sub-Clause and replace with:

“Not used. Any references to DAAB Agreement in the Contract shall be deemed null and void and have no legal standing between the Employer and the Contractor.”

8)	Sub-Clause 1.1.58 - delete the text next to the Sub-Clause and replace with:

“Not used. Any references to Provisional Sums in the Contract shall be deemed null and void and have no legal standing between the Employer and the Contractor.”

9)	Sub-Clause 1.1.67 - add sentence:

“The Site means the land area located in Turda, Cluj county, Romania, identified with cadastral no. 66330, registered with Turda Land Book no. 66330, having a surface of 375.861 sqm (with any further amendments, if case).”

10) 	Sub-Clause 1.1.77 - delete the text next to the Sub-Clause and replace with:

“Unforeseeable” means not reasonably foreseeable and against which adequate preventive precautions could not reasonably be taken by an experienced Contractor by the Contract date.”

11) 	Sub-Clause 1.1.79 – delete the text next to the Sub-Clause and replace with:

“Works” mean the Permanent Works and the Temporary Works, as well as all works, services, manpower, design, permitting, deliveries of goods, materials, equipment, maintenance, supervision, inspections, testing, training, drawing-up and delivery of requested documentation and any other works and services to be provided by the Contractor as set forth in the Contract and in the Employer’s Requirements.”

12)	Sub-Clause 1.2 – add at the end of the Sub-Clause the following text:

“Application of the “contra proferentem” rule is excluded.

If a provision is or becomes illegal, invalid or unenforceable, that will not affect the legality, validity or enforceability of any other provision and the Parties shall soonest discuss and agree an alternative text that comes in with the same effect but that is legal, valid and enforceable.”

13)	Sub-Clause 1.12 – implement the following amendments:

- delete sub-paragraph (a) and replace with:

“(a) The Employer has obtained the ATR, the building permit for the execution of the Permanent Works and will obtain the establishment authorization. Any other permits, permissions, licenses and/or approvals that are necessary for the execution or in relation to the Works shall be obtained by the Contractor, on Contractor’s expense, but on Employer’s behalf.”

- delete sub-paragraph (d) and replace with:

“(d) the Contractor shall comply with all permits, permissions, licences and/or approvals obtained by either the Employer and/or the Contractor”.

- delete the second paragraph;

- add the following text at the end of Sub-Clause:

“All permission(s), permits, licences and / or approvals which at any time are required in view of/for the delivery, (temporary) import and/or (re)export (including clearance through customs) of any Goods and / or the execution of the Works shall be obtained by the Contractor and the Contractor shall indemnify and hold the Employer harmless against and from the consequences of any failure to do so. In case the Law imposes that any taxes, duties and fees must be paid directly by the Employer then all these costs shall be invoiced back by the Employer to the Contractor and paid by the latter within 15 (fifteen) days following the receipt of the invoice and in case the Contractor does not pay such invoices, the Employer may off set the respective value from the amounts due to the Contractor from the Contract Price.”

14)	Sub-Clause 1.14 – in first paragraph delete sub-paragraphs (b), (c) and (g).

15)	Sub-Clause 2.2 - delete the entire text and replace with:

“The Employer shall (where applicable) provide reasonable assistance to the Contractor at the request of the Contractor for the Contractor’s applications for any permits, licences or approvals required by the Laws of the Country which the Contractor is required to obtain under Sub-Clause 1.12.

16)	Sub-Clause 2.4 - delete the entire text as being not applicable.

17)	Sub-Clause 2.5 – delete the entire text and replace with:

“The Employer made available to the Contractor for his information, prior to signing date of the Contract, all relevant data in the Employer’s possession on sub-surface and hydrological conditions at the Site, including environmental aspects. The Employer shall similarly make available to the Contractor all such data which come into the Employer’s possession after the signing date of the Contract. The Contractor shall be responsible for interpreting all such data. The Employer shall have no responsibility for the accuracy, sufficiency or completeness of such data and/or items of reference.

The Contractor shall be fully responsible for performing an analysis of the soil quality and to determine the specific technical conditions required for foundations.

The Contractor shall be deemed to have obtained all necessary information as to risks, contingencies and other circumstances which may influence or affect the Works. The Contractor shall be deemed to have inspected and examined the Site, its surroundings, the above data and other available information, and to have been satisfied before entering into this Contract as to all relevant matters, including (without limitation):

(a) the form and nature of the Site, including sub-surface conditions,

(b) the hydrological and climatic conditions,

(c) the extent and nature of the work and Goods necessary for the execution and completion of the Works and the remedying of any defects,

(d) the Laws, procedures and labour practices of the Country, and

(e) the Contractor’s requirements for access, accommodation, facilities, personnel, power, transport, water and other services.”

18)	Sub-Clause 2.6 – delete the entire text as being not applicable

19)	Sub-Clause 4.4 – delete the text of the first paragraph and replace with:

“The Contractor shall not subcontract any part of the Works without the Employer’s prior written approval.”

20)	Sub-Clause 4.5 – delete the entire text of the Sub-Clause as being not applicable

21)	Sub-Clause 4.6 – delete the last paragraph of the Sub-Clause.

22)	Sub-Clause 4.22 – add sentence at the end of the Sub-Clause with the following text:

“The Contractor or any of the Subcontractors may not erect or append any whatsoever publicity boards upon the Site or against the Site fences, except with the prior approval of the Employer’s Representative”.

- Sub-Clause 4.23 – implement the following amendments:

- The first paragraph of the Sub-Clause is replaced by the following text:

- "In accordance with the applicable law, all fossils, coins, articles of value or antiquity, and structures and other remains or items of geological or archaeological interest found on the Site are the property of the Romanian State and will be entrusted by the Contractor under the care and authority of the competent state authorities and the Contractor will be responsible to take all necessary measures in this respect, on Contractor’s cost. The Contractor shall take all reasonable precautions to prevent Contractor’s Personnel or other persons from removing or damaging any of these findings".

- Last paragraph of the Sub-Clause is deleted

24)	Sub-Clause 5.1 – delete the last paragraph of the Sub-Clause as being not applicable.

25)	Sub-Clause 5.5 – “Training” is applicable and shall produce effects. The Contractor shall carry out the training of the employees of the Employer, as provided in the Sub-Clause and according to the provisions under the Employer’s Requirements.

26)	Sub-Clause 5.6 – “As-Built Records” is applicable and shall produce effects as per the provisions of the Sub-Clause and according to the provisions under the Employer’s Requirements.

27)	Sub-Clause 5.7 – “Operation and Maintenance Manuals” is applicable and shall produce effects as per the provisions of the Sub-Clause and according to the provisions under the Employer’s Requirements.

28)	Sub-Clause 7.6 – in third paragraph, delete the sub-paragraph (ii) [“an Exceptional Event….”].

29)	Sub-Clause 8.1 – in second paragraph, the Commencement Date shall be within 14 days after the date on which the Contract comes into full force and effect as per the Contract Agreement.

30)	Sub-Clause 10.1 – in first paragraph add the following sub-paragraphs:

“(f) 	the Employer has received the complete technical book of construction, as defined in the applicable Laws;

(g) 	the minutes upon completion of works with the local authorities according to the Government Decision no. 343/2017 (in Romanian: proces verbal de receptie la terminarea lucrarilor) have been dully executed in accordance with applicable legislation and, according to the provisions of such minutes, the Works are accepted;

(h) 	the complete and correct documentation has been prepared by the Contractor and filed with the competent authority in view of issuance of the fire permit for the Project;

(i) 	all guarantees of the Contractor for the quality of the Works performed and all guarantees of the manufacturers for the equipment, systems and any other goods installed and/or incorporated in the Project have been delivered to the Employer and are in full force and effect;”

31) 	Sub-Clause 11.9 – the second paragraph is deleted and replaced with:

“The Employer shall issue the Performance Certificate to the Contractor within 28 days after the latest of the expiry dates of the Defects Notification Period or as soon thereafter as the Contractor has cumulatively fulfilled all conditions mentioned below:

- Supplied all the Contractor's Documents and, if applicable, the Employer has given (or is deemd to have given) a Notice of No-objection to the as-built record sunder sub-paragraph (b) of Sub-Clause 5.6 [As-Built Records]; and

- All Works described in the Employer’s Requirements, including without limitation the Operation and Maintenance services, have been duly completed;

- All tests described in the Employer’s Requirements have been duly completed (including remedying any defects) without any objections/claims from the Employer in accordance with the Contract and the Tests after Completion have been successfully done meeting the minimum Guaranteed Production, Performance Ratio and Availability over the periods of analysis, as such are defined in the Employer’s Requirements;

- Training of Employer’s Personnel is completed, as provided in the Employer’s Requirements;

- Sub-Clause 11.10 – add the following paragraph at the end of the Sub-Clause:

“The Defects Notification Period and the term mentioned in the sub-paragraph above do not limit or exclude the application of the provisions of Law 10/1995 art. 23, art. 25 and art. 30”.

33)	Sub-Clause 12.1 – “Procedure for Tests after Completion” is applicable and shall produce effects as per the provisions of the Sub-Clause 12.1 and according to the provisions of the Employer’s Requirements. In second paragraph of the Sub-Clause 12.1, timing of the Tests after Completion shall be as stipulated in the Employer’s Requirements.

34)	Sub-Clause 13.3.1 – delete last sentence of the second paragraph of the Sub-Clause [“If the Parties have agreed to the omission of any work ………..as a result of the omission”];

35)	Sub-Clause 13.3.2 – delete the last paragraph of the Sub-Clause;

36)	Sub-Clause 13.4 – [Provisional Sums] – delete the entire clause as being not applicable.

37)	Sub-Clause 13.7 – delete the entire text and substitute with the following:

“The Contract Price shall not be adjusted for an increase or decrease of the cost of labour, of Goods, materials, equipment and / or installations.”

38)	Sub-Clause 14.1 – add the following paragraph at the end of the Sub-Clause:

“The Contract Price is exclusive of VAT and includes all Works, services, manpower, Operation and Maintenance, Goods, equipment, machinery, hardware, products of any kind to be provided and included in the Works, as well as any other goods of the Contractor which is required to provide exclusively at his own expense and risk for the execution of the Works to be carried out in accordance with the Contract (including, but not limited to, the cost of the necessary utilities to carry out the Works, necessary Testing, the transport of materials, Contractor’s and its subcontractor’ staff costs, design costs, architecture, etc., and all related costs for all stages preceding the execution of the Works, but not limited to the Site organization, the security / guarding of the Site and the Works, the proper execution of the Works and the complete, functional and non-defective completion of the Project connected to utilities. To avoid any doubt, changes in the quantity of materials, price of materials, labour or any other item and / or service required to complete the Works will have no impact on the Contract Price. All duties, levies and / or taxes of whatever nature are included. The costs for the permissions (endorsements, permits, authorizations) which are necessary for the Works, as well as all taxes, duties and fees necessary for performing the Works are included in the Contract Price. Any bill of quantities is provided for information purposes only and any item of work not explicitly mentioned in the bill of quantities, but however needed to perform and complete the Works shall be considered included in the Contract Price.”

39)	Sub-Clause 14.4 – delete the entire text of the Sub-Clause as being not applicable.

40)	Sub-Clause 14.8 – delete the entire text and substitute with the following:

“If payments are delayed with more than 30 days from their due date, the Contractor shall be entitled to receive delay penalties in the amount stated in the Contract Data, per day of delay on the amount unpaid during the entire period of delay (starting with the first day of delay) and until full payment of the amount.

The Employer shall pay such penalties within 21 days as of the receipt of the Contractor’s notice in this respect.

Compounding of financing charges is excluded.”

41)	Sub-Clause 14.9 – implement the following amendments:

- replace the text of the first paragraph with the following text:

“After the issue of the Taking-Over Certificate for the Works and remediation of all outstanding work and defects listed in the Taking-Over Certificate (if case), referred to in Sub-Clause 10.1, the Contractor shall include the first half of the Retention Money in a Statement”.

- delete the last paragraph of the Sub-Clause.

42)	Sub-Clause 15.6 – delete sub-paragraph (b).

43)	Sub-Clause 16.1 – in second paragraph, replace “21 days” with “60 days”.

44)	Sub-Clause 16.2.1 – implement the following amendments:

- Replace “42 days” with “60 days” in subparagraph (b);

- delete sub-paragraphs (d) and (e)

- Sub-Clause 16.4 – delete sub-paragraph (b)

- Sub-Clause 17.2 – delete sub-paragraphs (d) and (e).

- Sub-Clause 17.5 – in sub-paragraph (b) replace reference to “any event described under sub-paragraphs (a) to (f) of Sub-Clause 17.2” with “any event described under sub-paragraphs (a), (b), (c) and (f) of Sub-Clause 17.2”.

- Sub-Clause 17.6 – in first paragraph replace reference to “any event described under sub-paragraphs (a) to (f) of Sub-Clause 17.2” with “any event described under sub-paragraphs (a), (b), (c) and (f) of Sub-Clause 17.2”.

- Sub-Clause 18.1 – add the following text at the end of the Sub-Clause:

“The provisions of art .1351 of the Romanian Civil Code regarding Force Majeure will prevail”

- Sub-Clause 18.2 – replace in second paragraph the term of “14 days” with “5 days”

- Sub-Clause 18.3 – replace in second paragraph the term of “28 days” with “14 days”

- Sub-Clause 18.4 – delete sub-paragraph (b)

- Sub-Clause 18.5 – delete sub-paragraphs (c), (d) and (e)

- Sub-Clause 19.2.1 – implement the following amendments:

- In first paragraph, add two new sub-paragraphs, numbered as (c) and (d), having the following content:

“(c) 	the cost of making good any part of the Works which is defective (including defective material and workmanship) or otherwise does not comply with the Contract, including the cost of making good any loss or damage to any other part of the works attributable to such defect or non-compliance;

(d) 	the risks arising from Exceptional Events”.

- In third paragraph, delete sub-paragraphs (i) and (iv);

- Sub-Clause 20.2 – delete any reference or provision in Sub-Clause 20.2 (and subsequent sub-clauses 20.2.1 – 20.2.7) related to the loss of the right/entitlement to claim or the discharge of liability of the other Party due to the late submission of a Notice of Claim or of a statement/other documentation pertaining to a Claim.

- Clause 21 – delete the entire Clause (and all its Sub-Clauses from 21.1 to 21.8) and include solely Sub-Clause 21.1 with the following text:

“If a dispute (of any kind whatsoever) arises between the Parties in connection with, or arising out of, the Contract or the execution of the Works, including any dispute as to any certificate, determination, instruction, opinion or valuation of the Employer’s Representative, either Party shall make all efforts in order to amicably settle by direct negotiations any disagreement or dispute that may arise out of or in relation to the contract fulfilment.

If, after 30 days from the beginning of such negotiations, the Contractor and the Employer fail to amicably settle a contractual disagreement, any dispute, controversy, or claim arising out of or in connection with this Contract, including with respect to the execution, performance or termination hereof, shall be finally settled by means of arbitration. The dispute shall be finally settled by institutional arbitration under the Rules of the Court of International Commercial Arbitration of the Romanian Chamber of Commerce and Industry (the “Court”), in accordance to its rules (the “Rules”), which are deemed to be incorporated by reference into this clause. The arbitral tribunal shall consist of three (3) arbitrators. Each party shall appoint one arbitrator, and the two arbitrators so appointed shall appoint the third arbitrator, who shall act as the chairman of the tribunal. If a party fails to appoint an arbitrator within the period prescribed by the Rules, or if the arbitrators appointed by the parties fail to agree on the third arbitrator, the appointment shall be made by the Court in accordance with its Rules.

The seat of arbitration shall be Bucharest, Romania.

The language of the arbitration shall be English.

The governing law shall be the substantive law of Romania.”

- Appendix – “General Conditions of DAAB Agreement” – is not applicable and shall produce no effects.

- Annex – “DAAB Procedural Rules” – is not applicable and shall produce no effects.

Signed by:

Employer							Contractor

RES INVEST SOUTH EAST EUROPE S.R.L.			……………………….